## Executive Dashboard
IT PROJECT MANAGEMENT ¦ EXECUTIVE PERFORMANCE DASHBOARD
CRM Implementation ¦ Corporate operating review ¦ Simulated/modelled portfolio data
User Adoption % 93.0% Target: 90.0% ¦ ON TRACK | Migration Accuracy % 99.1% Target: 98.0% ¦ ON TRACK |  |  | Duplicate Rate % 2.7% Target: 3.0% ¦ ON TRACK
UAT Pass Rate % 97.0% Target: 95.0% ¦ ON TRACK | Training Completion % 96.0% Target: 95.0% ¦ ON TRACK |  |  | Go-Live Sev-1 Defects 0 Target: 0 ¦ ON TRACK
EXECUTIVE READOUT |  | LEADERSHIP PRIORITIES
WHAT HAPPENED Modeled current performance is at or above the primary target set. WHY The project applies structured KPI governance, root-cause management, corrective action, and cross-functional accountability. NEXT Protect gains, investigate exceptions, validate data quality, and transition stable controls into business-as-usual governance. |  | Priority | Management Action | Owner | Due | Status | Decision / Evidence
|  | 1 | Protect target performance | Functional Lead | Next Review | In Progress | Monitor KPI exceptions and root causes
|  | 2 | Close remaining red/amber items | Workstream Owner | Next Review | In Progress | Document corrective actions
|  | 3 | Validate data quality | Analytics / Ops | Monthly | In Progress | Reconcile source and dashboard
|  | 4 | Sustain operating controls | Operations | 30 Days | Planned | Audit control adherence
|  | 5 | Transition stable controls to BAU | Leadership | 90 Days | Planned | Approve governance cadence

## KPI Data
KPI | Baseline | Target | Current | Direction | Variance | Attainment | Health
User Adoption % | 0% | 90% | 93% | higher | 3% | 100% | ON TRACK
Migration Accuracy % | 0% | 98% | 99.1% | higher | 1.1% | 100% | ON TRACK
Duplicate Rate % | 11% | 3% | 2.7% | lower | 0.3% | 100% | ON TRACK
UAT Pass Rate % | 0% | 95% | 97% | higher | 2% | 100% | ON TRACK
Training Completion % | 0% | 95% | 96% | higher | 1% | 100% | ON TRACK
Go-Live Sev-1 Defects | 0 | 0 | 0 | lower | 0 | 100% | ON TRACK

## Management Actions
Priority | Management Action | Owner | Due | Status | Decision / Evidence
1 | Protect target performance | Functional Lead | Next Review | In Progress | Monitor KPI exceptions and root causes
2 | Close remaining red/amber items | Workstream Owner | Next Review | In Progress | Document corrective actions
3 | Validate data quality | Analytics / Ops | Monthly | In Progress | Reconcile source and dashboard
4 | Sustain operating controls | Operations | 30 Days | Planned | Audit control adherence
5 | Transition stable controls to BAU | Leadership | 90 Days | Planned | Approve governance cadence