## Weekly_Data
Week | Milestone Completion % | Active User Adoption % | Migration Accuracy % | Duplicate Rate % | UAT Pass % | Training Completion % | Open Sev1 | Open Sev2 | Support Tickets | Avg Resolution Hours | Stakeholder Satisfaction
W1 | 10% | 0% | 0% | 11% | 0% | 0% | 0 | 0 | 0 | 0 | 3.4
W2 | 20% | 5% | 0% | 10.2% | 0% | 0% | 0 | 0 | 0 | 0 | 3.5
W3 | 30% | 12% | 96% | 8.8% | 35% | 0% | 0 | 2 | 0 | 0 | 3.6
W4 | 40% | 20% | 97.2% | 7.5% | 58% | 10% | 0 | 4 | 0 | 0 | 3.7
W5 | 50% | 32% | 98% | 6.2% | 74% | 35% | 0 | 5 | 0 | 0 | 3.8
W6 | 62% | 48% | 98.4% | 5.1% | 86% | 62% | 0 | 4 | 0 | 0 | 4
W7 | 73% | 64% | 98.7% | 4.3% | 92% | 78% | 0 | 3 | 0 | 0 | 4.1
W8 | 84% | 78% | 98.9% | 3.6% | 95% | 90% | 0 | 2 | 18 | 9.5 | 4.2
W9 | 93% | 87% | 99% | 3.1% | 96% | 95% | 0 | 1 | 31 | 7.2 | 4.3
W10 | 100% | 93% | 99.1% | 2.7% | 97% | 96% | 0 | 0 | 22 | 5.8 | 4.5

## Executive_Dashboard
CRM IMPLEMENTATION ¦ EXECUTIVE PROJECT HEALTH REVIEW
KPI | Baseline | Target | Current | Variance | Attainment | Trend | Health
Milestone Completion % | 0% | 100% | 100% | 0% | 100% | 100% | ON TRACK
Active User Adoption % | 0% | 90% | 93% | 3% | 100% | 93% | ON TRACK
Migration Accuracy % | 0% | 98% | 99.1% | 1.1% | 100% | 99.1% | ON TRACK
Duplicate Rate % | 11% | 3% | 2.7% | 0.3% | 100% | 8.3% | ON TRACK
UAT Pass % | 0% | 95% | 97% | 2% | 100% | 97% | ON TRACK
Training Completion % | 0% | 95% | 96% | 1% | 100% | 96% | ON TRACK
Open Sev-1 | 0 | 0 | 0 | 0 | 1 | 0 | ON TRACK
EXECUTIVE COMMENTARY | [6 empty] | TOP PRIORITIES | Owner | Due | Status | Management Response
WHAT HAPPENED: Modeled Week 10 reached go-live and adoption targets. WHY: Controlled scope, data cleansing, staged UAT, role-based training, and formal go/no-go gates reduced delivery risk. WHAT WE ARE DOING: Transition to 30-day hypercare, monitor adoption/data quality, and transfer the enhancement backlog. DECISION NEEDED: Approve hypercare exit criteria and steady-state CRM governance. | [6 empty] | Stabilize post-launch support | CRM Admin | W11 | In Progress | Daily triage and aging review
[7 empty] | Protect adoption | Sales Ops | W12 | In Progress | Manager coaching for low-usage teams
[7 empty] | Control data quality | Data Owner | W12 | In Progress | Duplicate and required-field audit
[7 empty] | Transfer backlog | System Owner | W13 | Planned | Prioritize deferred enhancements

## RAID_Log
ID | Type | Description | Probability | Impact | Score | Owner | Response | Due | Status
R-01 | Risk | Source data quality delays migration | 4 | 5 | 20 | Data Lead | Cleanse early; exception queue | W5 | Controlled
R-02 | Risk | Low user adoption | 3 | 5 | 15 | Sales Ops | Role training; manager reinforcement | W12 | Controlled
R-03 | Risk | Integration failure at cutover | 2 | 5 | 10 | Tech Lead | Regression test; rollback plan | W10 | Controlled
I-01 | Issue | Duplicate records above threshold | 4 | 4 | 16 | Data Lead | Merge rules and audit | W9 | Closed
D-01 | Dependency | Identity/access provisioning | 3 | 4 | 12 | IT Admin | Provisioning checklist | W9 | Closed
A-01 | Assumption | Business owners available for UAT | 2 | 4 | 8 | PM | Calendar lock and backup testers | W8 | Validated

## Action_Plan
ID | Workstream | Action | Owner | Start | Due | Priority | Dependency | Status | Evidence
A01 | Discovery | Confirm requirements and process map | PM | W1 | W2 | High |  | Complete | Signed baseline
A02 | Data | Profile and cleanse 4,800 records | Data Lead | W2 | W5 | High | A01 | Complete | Reconciliation report
A03 | Configuration | Configure workflows and roles | CRM Admin | W3 | W6 | High | A01 | Complete | Config checklist
A04 | Testing | Execute integration/UAT cycles | Test Lead | W5 | W8 | High | A02/A03 | Complete | UAT report
A05 | Training | Deliver role-based training | Change Lead | W7 | W9 | High | A04 | Complete | Completion log
A06 | Cutover | Execute migration and go/no-go | PM | W9 | W10 | Critical | A02-A05 | Complete | Go-live approval
A07 | Hypercare | Run daily support triage | CRM Admin | W10 | W12 | High | A06 | In Progress | Ticket dashboard
A08 | Handoff | Transfer governance/backlog | System Owner | W12 | W13 | Medium | A07 | Planned | Handoff sign-off

## UAT_Defects
Test ID | Area | Scenario | Severity if Failed | Owner | Result | Defect ID | Retest | Disposition
UAT-01 | Lead | Create and assign lead | Sev-2 | Sales SME | Pass |  |  | Accepted
UAT-02 | Opportunity | Advance stage with exit criteria | Sev-2 | Sales SME | Pass |  |  | Accepted
UAT-03 | Data | Duplicate detection | Sev-2 | Data SME | Pass | DEF-12 | Pass | Closed
UAT-04 | Reporting | Manager pipeline dashboard | Sev-2 | Manager SME | Pass |  |  | Accepted
UAT-05 | Access | Role-based permissions | Sev-1 | IT SME | Pass | DEF-15 | Pass | Closed
UAT-06 | Integration | Activity synchronization | Sev-1 | Tech SME | Pass |  |  | Accepted

## RACI
Deliverable | Sponsor | PM | Sales Ops | CRM Admin | Data Lead | Test Lead | Change Lead
Requirements | I | A/R | R | C | C | C | C
Data Migration | I | A | C | R | R | C | I
Configuration | I | A | C | R | C | C | I
UAT | I | A | R | C | C | R | C
Training | I | A | R | C | I | I | R
Go/No-Go | A | R | C | C | C | C | C
Hypercare/Handoff | I | A | R | R | C | C | R

## Cutover_Checklist
Step | Activity | Owner | Planned Window | Dependency | Evidence | Status | Rollback Trigger
1 | Freeze source extracts | Data Lead | W10 D-1 | Data approval | Frozen files | Complete | Unauthorized changes
2 | Final production load | CRM Admin | W10 D0 | Step 1 | Load log | Complete | Load failure
3 | Reconcile records | Data Lead | W10 D0 | Step 2 | Reconciliation | Complete | Accuracy <98%
4 | Smoke test | Test Lead | W10 D0 | Step 3 | Test results | Complete | Critical workflow fails
5 | Business validation | Sales Ops | W10 D0 | Step 4 | Approval | Complete | Business blocker
6 | Go/no-go | Sponsor/PM | W10 D0 | Steps 1-5 | Decision log | Complete | Any gate fails
7 | Open production | CRM Admin | W10 D0 | Step 6 | Launch notice | Complete | Critical outage
8 | Start hypercare | Support Lead | W10 D+1 | Step 7 | Triage log | In Progress | N/A

## Change_Log
CR ID | Request | Requester | Scope Impact | Schedule Impact | Risk | Recommendation | Approver | Decision | Rationale
CR-01 | Add custom forecast field | Sales Ops | Low | Low | Low | Approve | Sponsor | Approved | Supports reporting
CR-02 | Add advanced automation before launch | Sales Manager | High | High | High | Defer | Sponsor | Deferred | Protect critical path
CR-03 | Expand historical migration | Business Owner | High | Medium | Medium | Defer | Sponsor | Deferred | Low near-term value
CR-04 | Add duplicate alert | Data Lead | Low | Low | Low | Approve | PM | Approved | Supports quality target